- PROJECT  IDENTIFICATION

- PROJECT  TITLE :  Extra Virgin Coconut Oil  Project

- PROJECT  SITE  :  Tabaco City and Libon, Albay Province

- PROJECT  TYPE :  Livelihood Development

Capability Building

- BENEFICIARIES :  NACI Members and Affiliates in Tabaco and Libon

Coconut  Farmers

- PROPONENT : Nationwide Association Of Consumers (NACI), Inc.

Region 5 Chapter

Tayhi, Tabaco City

Contact Person : IRMA BUENCONSEJO - BIBOSO

Regional Coordinator

Tayhi, Tabaco City

Email : naciphil@yahoo.com

- PARTNER : Nationwide Association Of Consumers (NACI), Inc. - Main Unit

240 Narra Street, Marikina Heights, Marikina City

Tel / Fax 941-5417

Contact Person : Moises  P. Talladen

Secretary General

Mobile Phone No. 09197069551

E-mail : moisestalladen@yahoo.com

- DURATION : Six Months and Continuing

- INITIAL  BUDGET : Two  Million  Pesos ( Php 2,000,000 )

- EXECUTIVE SUMMARY

  - THE ORGANIZATION

The Nationwide Association Of Consumers (NACI), Inc. is a non-stock, non-government organization (NGO) registered with the Securities & Exchange Commission (SEC) with SEC Registration No. ANO94-002719 dated July 20, 1994. It is the only consumer organization of national stature that has been accredited, so far, by the Department of Trade & Industry with Accreditation Certificate No. 01 dated November 12, 2003.

The organization's main advocacy is Consumer Welfare and Economic Empowerment of Consumers. " We believe that the best protected consumer is one who is  economically empowered and well informed ".

NACI operates through its regional and provincial chapters nationwide, and also through its affiliated organizations, mostly Cooperatives, in the provinces. It provides technical assistance to its members and affiliates in terms of the following:

- develops feasibility studies and project proposals for economic empowerment;

- conducts training and  seminars on Consumer Rights & Responsibilities, and on issues of concern relevant to consumer welfare & protection.

- transfers livelihood technology for local implementation;

- represents its members in public hearings and conferences on matters that affect consumer welfare;

- represents its aggrieved members in dispute resolutions through the mediation of the Dep't of Trade & Industry (DTI), or Securities & Exchange Commission (SEC), or  any concerned government agency.

In this particular project, NACI addresses Consumer Right No. 1: " The right of consumers to basic needs "( food, shelter, clothing, education, etc.).

  - THE  PRODUCT

The extra virgin coconut oil (evco) is produced from the cold-pressed extract of  matured coconut  meat or kernel by purely mechanical method. The term " extra virgin" is borrowed from the  " extra virgin olive oil" which is produced in similar fashion. The extra virgin coconut oil produced in this project differs significantly from most virgin coconut oils (vco) presently available in the market in terms of processing ( vco is low-heat treated, while evco is not ), consistency ( vco is thicker ), aroma and taste (evco tastes better). Laboratory analysis through Gas-Liquid Chromatography will settle the issue on the chemical composition of both products. Both oils, however, look  the same as clear white oil.

The principal uses of  virgin coconut oil are the following:

- as the cooking oil of choice by health-conscious consumers especially those with cardio-vascular illness;

- basic ingredient in the manufacture of soap, shampoo, cosmetics and skin care products;

- as carrier or base oil in the making of  therapeutic oils ( mixed with essential oils) used for aromatheraphy in the Spa industry;

- diesel fuel substitute ( coco methyl ester or coco diesel);

- as anti-microbial medicine in bacterial, fungal and viral infections such as HIV, Herpes, Cytomegalovirus, STD, dandruff, and skin infections.

The by-products from the manufacture of  extra virgin coco oil can be re-processed into  a.) coconut flour,  b.) animal feeds and  C.) charcoal. These can be produced in commercial quantities to provide additional income for the organization and its beneficiaries.

  - THE INVESTMENT

NACI requires funding from investors or funding agencies to carry out a sustainable enterprise for its members and affiliates in the provinces where coconuts abound all year round. This project is designed to produce high quality, cold-pressed extra virgin coco oil that  meets current demand and, eventually, the growing demand in foreign markets.

The required budget is two million pesos (Php 2,000,000.00) for the initial 6 month - operation. This project is expected to become self-sustaining after a successful first six months. The proposed application of  funds is to

- acquire fixed assets in terms of equipments and infrastructures ( cold-presses, graters, dryer, centrifuge, warehouse & work station, etc.);

- obtain organic certification of  the raw resource ( coconut plantation );

- provide the initial working capital for project administration and marketing.

  - SALES  FORECAST

The following is the projected gross sales  from extra virgin coco oil over a five year period ( refer to the attached Projected Income Statement ).

Year 1            Year 2             Year 3             Year 4             Year 5             Total

20.1 million    25.2 million      31.5 million     39.4 million     49.2 million    165.4 million

Substantial additional income will be generated from the sales of by-products such as coconut flour, charcoal, animal feeds and skin care products.

  - RETURN ON INVESTMENT

Year 1           Year 2              Year 3              Year 4             Year 5

268.20%        342.48%          436.98%          555.45%          703.95%

  - EXPECTED  RESULTS

- Substantial income for the member-participants  in this project;

- Additional income for coconut farmers in Tabaco City and Libon;

- Establishment of new business opportunities for unemployed women and various affiliated organizations;

- Transform the project sites into  progressive centers of  economic growth;

- Contribute to our country's  production of   indigenous coco diesel for local use.

3.  PROJECT DESCRIPTION

  - BUSINESS BACKGROUND

Recent scientific findings on the health benefits of  virgin coconut oil contributed to the current demand and interest on the product, both locally and internationally. Studies have shown that virgin coco oil has effective anti-microbial actions against certain types of  bacteria, fungi and viruses such as Aids virus, herpes, cytomegalovirus, hepatitis, flu virus, etc. When used as cooking oil, it has been found to be beneficial for people with cardio-vascular ailments ( heart disease, high blood, etc.), contrary to western belief. Its saturated fats is mostly  medium chain triglyceride which is completely metabolized in the human body, and does not contribute to the build-up of cholesterol and destructive free radicals, unlike other fats and oils.

Today, many Filipino entrepreneurs have embarked on the manufacture of virgin coco oil to supply growing demand.  With coconut trees growing all over the country, this business enterprise is quite easy to undertake as the technical and supply requirements are cheaply  available.

  - THE MANUFACTURING PROCESS

The Nationwide Association of Consumers (NACI), Inc. has developed its own cold - press technology in the production of  extra virgin coco oil.  The process is actually a simple one involving the following steps:

- Dehusking, grating, pressing and filtering;

- Ferment the cream or milk to separate the oil from the water. A clear, white oil develops on top of the solid part with the water at the bottom;

- Take out the oil, and place it in separate container;

- Place the oil in a centrifuge to remove the remaining water and protein;

- The final product is a clear white oil with a thin consistency and fresh coconut aroma.

This is the NACI Extra Virgin Coconut Oil ( NEVCO) ready for the market.

  - PRODUCT DEVELOPMENT

Six months after the onset of oil production, the organization will embark on project expansion by  producing:

- Coconut flour  from the dried kernel after extraction of  its milk;

- Coco diesel or Coconut Methyl Ester (CME) for local use;

- Virgin Coco Oil with Lemongrass Essential Oil  as a more effective anti-microbial/ anti-bacterial medicine than pure Virgin Coco Oil;

- Herbal soap and herbal shampoo, using our own virgin coco oil and lemongrass essential oil with its hydrolat produced by our sister organization, Gold In Grass Corporation.

Women Cooperatives in Albay will be organized to handle each of the above project components. The Training Department of NACI will conduct training seminars and transfer of technology in collaboration with Technicians from the Philippine Coconut Authority (PCA) and Technology & Livelihood Resource Center (TLRC). The Department Of Trade & Industry with whom NACI has signed a Memorandum of Agreement (MOA), will assist in the marketing of the products locally and internationally.

  - SALES AND PROMOTION

NACI  will participate in various Trade Exhibits nationwide such as those held in the following venues :

- World Trade Center - Metro Manila

- Phil. Trade & Training Center - Metro Manila

- Mega Trade Hall, SM Megamall - Metro Manila

- Provincial Trade Fairs - various provinces

- Hotels and Tourism outlets

A  website in the internet will be opened for promoting our products worldwide.

Initially, the participants and beneficiaries of this project will buy some of the products for their own consumption. The bulk , however, will be sold to the mother organization,NACI, for sales distribution to various chapters and affiliated organizations nationwide.

Export sales will be done  sometime in the future when production capacity shall have reached 5,000 liters of  virgin coco oil per month.

  - FUNDING  REQUIREMENTS

The funds required for this project will be used for the following:

Cost ( Php )

- acquisition of equipment & gadgets such as

- cold presses - 15 units;  dehuskers - 15 units;  graters - 15 units          155,000

- 4 gallon Orocan receptacle - 10 units                                                         2,000

- 4 gal Aluminum receptale with cover - 15 units                                          6,000

- 2.5 liter glass bowls with cover - 60 pcs.                                                     6,000

- 0.5 liter wide-mouthed glass bottles with cover - 300 pcs.                          9,000

- 0.5 liter plastic bottles with cap - 2000 pcs.                                                 8,000

- 250 ml plastic bottles with cap - 4000 pcs.                                                12,000

- 120 ml plastic bottles with cap - 1000 pcs.                                                  3,000

- Centrifuge - 1 unit                                                                                      70,000

- 12 cu. ft.  Refrigerator (3 units) and  Freezers                                           70,000

- Computer with printer - 1 unit                                                                    45,000

- Ink Cartridges - 5 pcs.                                                                                  6,000

- Label papers - 5 reams                                                                                1,000

- Electric fans ( 12" blade ) - 10 units                                                             5,000

- Stand fans (14" blade) - 5 units                                                                    5,000

- Air Blowers (14" blade) - 4 units                                                                   4,000

- 15 units each of the following measuring gadgets:

250 ml graduated cylinders, 2.5 ml glass droppers,                               12,000

250 ml glass funnels, 250 ml beakers, and steering rods                      13,000

- 1 unit Jeepney (2nd-hand) for transporting coconuts to work station       150,000

- Construction of

- Warehouse & Work Station ( 7 meters x 10 meters )                               400,000

- Working tables (15 units), benches (45 units)                                              7,000

- Storage Cabinets (15 units)                                                                          7,000

- Drying Chamber ( Dryer ), 2 cu. meters                                                      20,000

- Organic Certification of  Coconut plantation site                                         15,000

- Training of participants / beneficiaries                                                           5,000

- Marketing operation                                                                                  100,000

- Working Capital for  administration,salaries of  core personnel, and

buying of coconuts from farmers.                                                             900,000

Total Funding required ( for the first six months)                    Php 2,036,000

  - PROJECT IMPLEMENTATION

Time Frame                         Activity                                                   Responsibility

| 1st month | Procure required equipments & materials | MPT, ABZ |
| --- | --- | --- |
| 1st month | Construct warehouse / work station | MPT, IBB |
| 2nd month | Train the participants / beneficiaries | MPT |
| 2nd month | Sign supply contract with coconut farmers | IBB, JPP |
| 3rd month | Hire & train office employees | IBB, JRB |
| 4th month | Start production of extra virgin coconut oil (NEVCO) | MPT |
| 4th month | Laboratory analysis of NEVCO at DOST | ABZ |
| 4th month | Register the NEVCO at BFAD | MPT |
| 5th month | Inventory of produced NEVCO | IBB, ABZ |
| 5th month | Start sales / distribution to NACI Chapters nationwide | JPP, IBB |
| 6th month | Training on production of coconut flour | MPT |
| 6th month | Promote virgin coco oil at Trade Exhibits | MDL, ABZ |
| 6th month | Training on Charcoal - making | JRB |
| 7th month | Training on Soap & Shampoo - making | NKPT, IBB |
| 7th month | Training on production of skin care products | MPT, NKPT |
| 8th month | Training on production of coco -diesel fuel | MPT, JRB |

Legend :

MPT  - Moises P. Talladen                      MDL  - Matilda D. Lucero

ABZ  -  Alwin B. Zacarias                         JPP  -  Jose P. Pepito

JRB  -  Jose R. Baligod                            NKPT - Neva Kares P. Talladen

IBB   -  Irma B. Biboso

  - VIABILITY  AND  SUSTAINABILITY

The huge market demand for virgin coconut oil is fast growing as the population grows, and as more people learn about its benefits.  In fact, the current demand is so high that prices have been driven upwards. The selling price in the local market ranges from Php 500 to Php 600 per liter. As more supplies get into the market, the price is expected to go down.

The expected income from the sales of NEVCO shows the viability  of this project. This project will sustain itself after we start selling NEVCO in the market by the 4th month. The income is expected to grow substantially after we start producing the by-products such as coconut flour, charcoal, skin care products, animal feeds and coco diesel.

  - CONCLUSION

This project will provide sustainable enterprise and self-employment to many members who will actually become business partners of NACI. They need no longer seek  employment elsewhere as this project enables them to earn substantial income.

The coconut farmers in Albay will surely have a steady substantial income by selling their coconuts to the organization. As production requirement grows, more coconut farmers will be involved including those in  the nearby towns of Polangui, Ligao and Legaspi  as NACI will also buy their coconuts. Compared to their copra income which is presently at Php 11.00 per kilo of dried kernel, these farmers will be much better off selling their coconuts to NACI at  Php 3.00 per nut which can be translated to Php 15.00 - 20.00 per kilo of dried kernel without the trouble of cutting and drying expense that they would have with copra preparation.

Expansion of  this operation is planned in the immediate future to pursue the advocacy of NACI  on "economic empowerment " among its members nationwide. The profits that NACI shall earn from this operation will fund the setting up of work stations in the following sites within the next  five years:

- Barangays Tamurong and Calongboyan, Candon, Ilocos Sur

- Barangay Bacquit, Bauang, La Union

- Barangay Becques, Tagudin, Ilocos Sur

- Lucena City and Mauban, Quezon

- Sorsogon City, Sorsogon

By the end of a ten-year period, NACI shall have implemented a socio-economic development program nationwide that shall have contributed substantially to the attainment of  President Arroyo's objectives on job creation and support for new entrepreneurs. A modest estimate of NACI's contribution to the attainment of the President's 10 million job-objective would be between  one to two million new jobs from this project alone and its components by  year 2010.

Praise God Almighty!!!

4.  PROPOSAL  TO PROSPECTIVE  INVESTORS

Investors are invited to become partners of  NACI in implementing this project . Available investment options are offered as follows:

Investment Option A

Provide the funding required for  the first six (6) months in the amount of  two million pesos (Php 2,000,000 ). Investor(s) shall own fifty percent (50%) of  the  net  income for the first two years. This can be renewed for  a  new project site.

Investment Option B

Provide the funding required for a 12-month operation in the amount of four million pesos (Php 4,000,000). Investor(s) shall own eighty percent (80%) of  the net income for the first two years. This can be renewed for a new project site.

Investment Option C

Provide the initial funding in the amount of  two million pesos (Php 2,000,000);

Provide the coconut plantation that can supply 62,000 mature nuts every month, enough to produce,at least, 3,000 liters of virgin coconut oil in one month. The investor shall own seventy percent (70%) of the net income for the first two years. This can be renewed every year thereafter.

Prepared by :

MOISES  P. TALLADEN, Secretary General

and

JOSE  R. BALIGOD, Chairman